## Overview
Overview | Total time all weeks' tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Total Type 0 Tasks (hours) | Total Type 1 Tasks (hours) | Total Type 2 Tasks (hours) | Total Type 3 Tasks (hours) | Total Type 4 Tasks (hours) | Total Type 5 Tasks (hours) | Total Type 6 Tasks (hours)
Danny Chiu | 103 | 67 | 36 | 2 | 13 | 0 | 0 | 6 | 46 | 0
Brian Kabuye | 129 | 129 | 0 | 62 | 49 | 14 | 4 | 0 | 0 | 0
Raymond Wu | 116 | 96 | 20 | 89 | 7 | 0 | 0 | 0 | 0 | 0
Ayodele Awoleye | 124 | 122 | 2 | 31 | 5 | 0 | 26 | 0 | 36 | 24
Josh Wildey | 140 | 140 | 0 | 30 | 6 | 12 | 39 | 2 | 24 | 27
Total Hours Spent: | 472

## Danny
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 5 | 4 | 1 | 0-reviewed GIT and Android Studio 1-review project management tool website 2- 3- 4- 5-Initalized weekly reports and meeting minutes. 6- | 2 | 1 |  |  |  | 1
02/03/2016 - 02/09/2016 | 11 | 10 | 1 | 0- 1-defined our basic requirements 2- 3- 4- 5-updated SPPP and prepared presentation slides 6- |  | 2 |  |  |  | 8 |  | -Coordinate with Brian and Raymond to make sure we have an Android development environment -Cordinate with Ayodele and Josh to get our backend started. | 8
02/10/2016 - 02/16/2016 | 6 | 4 | 2 | 0- 1-revised user stories on Pivotal Tracker 2- 3- 4- 5-Reviewed SPPP 6- |  | 2 |  |  |  | 2
02/17/2016 - 02/23/2016 | 6 | 5 | 1 | 0- 1-revised user stories, pulled in main repository for android app 2- 3- 4- 5- 6- |  | 5
02/24/2016 - 03/01/2016 | 6 | 5 | 1 | 0- 1- 2- 3- 4- 5-Revised SPPP 6- | [5 empty] | 5
03/02/2016 - 03/08/2016 | 4 | 3 | 1 | 0- 1-peer review 2- 3- 4- 5- 6- |  | 3
03/09/2016 - 03/15/2016 | 6 | 5 | 1 | 0- 1- 2- 3- 4- 5-updated SPPP, started SDD 6- | [5 empty] | 5
03/16/2016 - 03/22/2016 | 8 | 4 | 4 | 0- 1- 2- 3- 4- 5-updated SPPP, reviewed iteration goals 6- | [5 empty] | 4
03/23/2016 - 03/29/2016 | 6 | 0 | 6 | 0- 1- 2- 3- 4- 5-followed-up on progress of project. Preparing for QA testing 6-
03/30/2016 - 04/05/2016 | 12 | 6 | 6 | 0- 1- 2- 3- 4-testing current Android environment on Android Studio 5-worked on updating Pivotal Tracker 6- |  |  |  |  | 3 | 3
04/06/2016 - 04/12/2016 | 7 | 3 | 4 | 0- 1- 2- 3- 4- 5-Revised SPPP document. Started SDD document. Worked on Final Presentation slides 6- |  |  |  |  | 3
04/13/2016 - 04/19/2016 | 6 | 6 | 0 | 0- 1- 2- 3- 4- 5-Worked on Final Presentation slides 6- | [5 empty] | 6
04/20/2016 - 04/26/2016 | 20 | 12 | 8 | 0- 1- 2- 3- 4- 5-Worked on Final Presentation slides.Revised SPPP document 6- | [5 empty] | 12
Total Time Spent (hours): | 103

## Brian
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 8 | 8 |  | 0-Research and Android studio 1- Install android studio to computer 2- weekly meeting 3- 4- 5- 6- | 3 | 3 | 2
02/03/2016 - 02/09/2016 | 14 | 14 |  | 0- Implement Blueprint app layouts using android studio 1- setup layout, build and set up applicaiton on andorid device 2- Set up and deploy first android scripts to group3 repo 3- weekly meeting 4- 5- 6- | 4 | 4 | 4 | 2
02/10/2016 - 02/16/2016 | 15 | 15 |  | 0-Trouble shoot github as issues relating to privacy settings and accessiblity were locked 1- documenting and updating team on progress of first iteration 2- setting up more xml scripts for layouts basing on blueprint 3- weekly meeitng 4- 5- 6- | 5 | 4 | 4 | 2
02/17/2016 - 02/23/2016 | 10 | 10 |  | 0-redesigning layout of homepage as it wasnt consistent with standard requirements 1- fixing layout issues so as app is compatibilty to all android devices 2-weekly meeting 3- 4- 5- 6- | 4 | 4 | 2
02/24/2016 - 03/01/2016 | 12 | 12 |  | 0- connecting flow of layouts for user authetication, account set up and verification checks 1- documenting for group's awareness, working with josh(backend ) to connect front end with backend for first iteration 2-weekly meeting 3- 4- 5- 6- | 6 | 4 | 2
03/02/2016 - 03/08/2016 | 0 | 0 |  | out of town
03/09/2016 - 03/15/2016 | 6 | 6 |  | 0- update to back end code to handle to erro messaging 1- weekly meeting 2- 3- 4- 5- 6- | 4 | 2
03/16/2016 - 03/22/2016 | 8 | 8 |  | 0- restarted project due to issues with code deployment and git 1- weekly meeting 2- 3- 4- 5- 6- | 6 | 2
03/23/2016 - 03/29/2016 | 10 | 10 |  | 0- 1-weekly meeting 2-deployment to git new code changes and updates to UI 3- 4- 5- 6- | 6 | 4
03/30/2016 - 04/05/2016 | 12 | 12 |  | 0-Code changes to application so as to run on android device 1-weekly meeting 2- 3- 4- 5- 6- | 6 | 6
04/06/2016 - 04/12/2016 | 10 | 10 |  | 0-weekly meeting 1-worked with josh to get integrated front end with back end 2- 3- 4- 5- 6- | 6 | 4
04/13/2016 - 04/19/2016 | 12 | 12 |  | 0-weekly meeting 1-research on converting data sent to json user signi up 2- 3- 4- 5- 6- | 6 | 6
04/20/2016 - 04/26/2016 | 12 | 12 |  | 0-weekly meeting 1- Documentation 2- Test Case development 3- 4- 5- 6- | 6 | 6
Total Time Spent (hours): | 129

## Raymond
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 4 | 3 | 1 | 0-Set Up Android Studio development environment 1-Review Android Studio Programming 2- 3- 4- 5- 6- | 1 | 2
02/03/2016 - 02/09/2016 | 7 | 6 | 1 | 0-Design user interface for the requirement tracker function of the app 1- 2- 3- 4- 5- 6- | 6
02/10/2016 - 02/16/2016 | 8 | 7 | 1 | 0- Reviewed Android concepts 1- Researched Android testing tools 2- 3- 4- 5- 6- | 5 | 2
02/17/2016 - 02/23/2016 | 6 | 5 | 1 | 0-Reviewed Android concepts 1-Redesigned flowchat for user interface 2- 3- 4- 5- 6- | 4 | 1
02/24/2016 - 03/01/2016 | 3 | 2 | 1 | 0- Reviewed Android concepts 1- 2- 3- 4- 5- 6- | 2
03/02/2016 - 03/08/2016 | 4 | 3 | 1 | 0- Reviewed Android concepts 1- 2- 3- 4- 5- 6- | 3
03/09/2016 - 03/15/2016 | 8 | 8 | 0 | 0-Reviewed Android concepts 1-Developed interface for requirement tracker 2- 3- 4- 5- 6- | 6 | 2
03/16/2016 - 03/22/2016 | 26 | 22 | 4 | 0-developed the layout and basic front-end code for the requirement tracker 1- 2- 3- 4- 5- 6- | 22
03/23/2016 - 03/29/2016 | 19 | 16 | 3 | 0-developed the layout and basic front-end code for the requirement tracker 1- 2- 3- 4- 5- 6- | 16
03/30/2016 - 04/05/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
04/06/2016 - 04/12/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
04/13/2016 - 04/19/2016 | 6 | 6 |  | 0- Merge the code 1- 2- 3- 4- 5- 6- | 6
04/20/2016 - 04/26/2016 | 25 | 18 | 7 | 0- Work on the navigation between each page of the requirement tracker and merge the code 1- 2- 3- 4- 5- 6- | 18
Total Time Spent (hours): | 116
s

## Ayodele
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 4 | 3 | 1 | 0- Prepared Git Tutorial 1-Reviewed Project Mgmt Website 2- 3- 4- 5- 6- | 1 | 2
02/03/2016 - 02/09/2016 | 6 | 5 | 1 | 0- Get familiar with the python code 1- Setup Version Control environment for Project on Github 2- 3- 4- 5- 6- | 3 | 2
02/10/2016 - 02/16/2016 | 9 | 9 |  | 0- Start researching Python Rest API 1- 2- 3- 4- 5- Weekly Meeting 6- | 6 | 1 |  |  |  | 2
02/17/2016 - 02/23/2016 | 8 | 8 |  | 0- Learning about APIs in the Python environment 1- 2- 3- 4- 5-Weekly Meeting 6-Write user stories and project and upload to PivotalTracker | 5 |  |  |  |  | 1 | 2
02/24/2016 - 03/01/2016 | 11 | 11 |  | 0-Learning Python and Django 1- 2- 3- 4- 5-weekly meeting 6-Test modification of current code base(adding API functionality) | 6 |  |  |  |  | 2 | 3
03/02/2016 - 03/08/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/09/2016 - 03/15/2016 | 4 | 4 |  | 0-Learning Python and Django 1- 2- 3- 4- 5- 6-Testing API from external application | 3 | [5 empty] | 1
03/16/2016 - 03/22/2016 | 12 | 12 |  | 0- Learning Python 1- 2- 3- 4- 5- Weekend Meeting 6-Setting up Updated Project Environment | 3 |  |  |  |  | 5 | 4
03/23/2016 - 03/29/2016 | 14 | 14 |  | 0- Research django api development 1- 2- 3- Enable get requests for some data objects(e.g userstories over the url 4- 5- Weekly Meeting 6- | 2 |  |  | 6 |  | 6
03/30/2016 - 04/05/2016 | 17 | 17 |  | 0- learn more about api communication in django/python 1- 2- 3-Enable get requests for some data objects over the url 4- 5- Weekly Meeting 6- | 2 |  |  | 9 |  | 6
04/06/2016 - 04/12/2016 | 17 | 17 |  | 0- 1- 2- 3- Add more functionalities to the Backend Server 4- 5-Weekly Meeting 6-Troubleshoot and fix bugs in the server code |  |  |  | 6 |  | 6 | 5
04/13/2016 - 04/19/2016 | 9 | 9 |  | 0- 1- 2- 3- Add more functionalities to the Backend Server 4- 5- 6-Troubleshoot and fix bugs in the server code |  |  |  | 5 |  |  | 4
04/20/2016 - 04/26/2016 | 13 | 13 |  | 0- 1- 2- 3- 4- 5- Final project Meeting 6- Worked on the Server documentation | [5 empty] | 8 | 5
Total Time Spent (hours): | 124

## Josh
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
02/03/2016 - 02/09/2016 | 5 | 5 |  | 0-Research Project and API for 3blueprints.com 1- 2- 3- 4- 5- 6- | 5
02/10/2016 - 02/16/2016 | 11 | 11 |  | 0-research Django 1- 2- 3-write code/research API for 3blueprints.com 4- 5-Weekly Meeting 6- | 4 |  |  | 5 |  | 2
02/17/2016 - 02/23/2016 | 6.5 | 6.5 |  | 0-research Django 1- 2- 3-write code/research API for backend site 4- 5-Weekly Meeting 6-Write User Stories for HW/upload to tracker | 2 |  |  |  |  | 1.5 | 3
02/24/2016 - 03/01/2016 | 20.5 | 20.5 |  | 0-research Django 1- 2- 3-write code/research API for backend site 4- 5-Weekly Meeting 6-Prepare presentation for Iteration 1 | 3 |  |  | 12 |  | 1.5 | 4
03/02/2016 - 03/08/2016 | 0 | 0 |  | Out of Town
03/09/2016 - 03/15/2016 | 3 | 3 |  | 0-research Django 1- 2-Manage Pivotol Tracker 3-write code/research API for backend site 4- 5-Weekly Meeting 6- | 2 |  | 0 | 1
03/16/2016 - 03/22/2016 | 21 | 21 |  | 0-research Rest Framework 1- 2-Manage Pivotol Tracker 3-write code/research API for backend site 4- 5-Weekly Meeting 6- | 5 |  | 1 | 8 |  | 7
03/23/2016 - 03/29/2016 | 10 | 10 |  | 0-research Rest Framework 1- 2-Manage Pivotol Tracker 3-write code/research API for backend site 4- 5-Weekly Meeting 6- |  |  | 1 | 2 |  | 7
03/30/2016 - 04/05/2016 | 11 | 11 |  | 0-Research App Development 1-Manage Pivotol Tracker 2-Diagram Generation 3-write code/help debug android app code 4-Testing 5-Weekly Meeting 6- | 3 | 2 |  | 5 |  | 1
04/06/2016 - 04/12/2016 | 11 | 11 |  | 0-Research App Development 1-Manage Pivotol Tracker 2-Diagram Generation 3-write code/help debug android app code 4-Testing 5-Weekly Meeting 6- | 3 | 2 |  | 4 | 1 | 1
04/13/2016 - 04/19/2016 | 16 | 16 |  | 0-Research App Development 1-Manage Pivotol Tracker 2-Diagram Generation 3-write code/help debug android app code 4-Testing 5-Weekly Meeting 6- | 3 | 1 | 8 | 2 | 1 | 1
04/20/2016 - 04/26/2016 | 25 | 25 |  | 0-Research App Development 1-Manage Pivotol Tracker 2-Diagram Generation 3-write code/help debug android app code 4-Testing 5-Weekly Meeting 6-Doumentation |  | 1 | 2 |  |  | 2 | 20
Total Time Spent (hours): | 140

## Mac
Week | Total actual time of this week tasks (hours) | Total Individual work time (hours) | Total meeting time (hours) | Task Breakdown | Type 0 Tasks (hours) | Type 1 Tasks (hours) | Type 2 Tasks (hours) | Type 3 Tasks (hours) | Type 4 Tasks (hours) | Type 5 Tasks (hours) | Type 6 Tasks (hours) | Estimated tasks for next week | Total estimated time (hours)
01/27/2016 - 02/02/2016 | 6.3 | 5.3 | 1 | 0- learning Mobile Application Security Requirements 1- Wrote Our Mobile Application Security Requirement general purpose 2- 3- 4- 5- 30 meeting with team ( 10 minutes before class and 20 during class) 6- | 3 | 2 |  |  |  | 0.3 |  | 7 | 5.3
02/03/2016 - 02/09/2016 | 7 | 6 | 1 | 0- Did research about Application Risk Management (Mobile App) 1- Wrote two pages Risk Management Analysis proposal for our project. In addition to worked on presenatation sildes with Danny (Team Lead) 2- 3- 4- 5- Communicate using Slack, email, and phone. 6- | 3 | 2 |  |  |  | 1 |  | 8 | 6
02/10/2016 - 02/16/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
02/17/2016 - 02/23/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
02/24/2016 - 03/01/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/02/2016 - 03/08/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/09/2016 - 03/15/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/16/2016 - 03/22/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/23/2016 - 03/29/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
03/30/2016 - 04/05/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
04/06/2016 - 04/12/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
04/13/2016 - 04/19/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
04/20/2016 - 04/26/2016 | 0 | 0 |  | 0- 1- 2- 3- 4- 5- 6-
Total Time Spent (hours): | 13.3